## ProjectTeam
Name | GitHub Alias
Bühler Ueli | smowdy
Jahn Tim Allan | ceoy
Kandiah Rajilatha | raji98
Klembowski Raphael | DerRaphe
Ristic Nikola | nristicBFH
Sutter Christoph | suttc1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login | The user has to login to use the app | low | 10h | 10h | 0h | waiting
2 | Basic Layout | Create navigation bar and initial layout of the app. | high |  |  |  | waiting
3 | Landing Page | The page the health visitor will see after a successful login. | high |  |  |  | waiting
4 | Patient Info Page | Display all the specified information about the patient | high |  |  |  | waiting
5 | Navigation | Handover of the necessary data to google maps for navigation | med |  |  |  | waiting
6 | Patient Report Page | Form to fill in after every visit | high |  |  |  | waiting
7 | Patient Report History | Display the history of all the reports of a specific patient | med |  |  |  | waiting
8 | Patient Evaluation | Form to fill in to create an evaluation | med |  |  |  | waiting
9 | Patient Evaluation History | Display the history of all evaluations of a specific patient | med |  |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180