## ProjectTeam
Name | GitHub Alias
Bühler Ueli | smowdy
Jahn Tim Allan | ceoy
Kandiah Rajilatha | raji98
Klembowski Raphael | DerRaphe
Ristic Nikola | nristicBFH
Sutter Christoph | suttc1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login | The user has to login to use the app | low | 10h | 10h | 0h | waiting
2 | Basic Layout | Create navigation bar and initial layout of the app. | high | 21h |  |  | waiting
3 | Landing Page | The page the health visitor will see after a successful login. | high |  |  |  | waiting
4 | Patient Info Page | Display all the specified information about the patient | high | 16h |  |  | waiting
5 | Navigation | Handover of the necessary data to google maps for navigation | med |  |  |  | waiting
6 | Patient Report Page | Form to fill in after every visit | high | 17h |  |  | waiting
7 | Patient Report History | Display the history of all the reports of a specific patient | med |  |  |  | waiting
8 | Patient Evaluation | Form to fill in to create an evaluation | med |  |  |  | waiting
9 | Patient Evaluation History | Display the history of all evaluations of a specific patient | med |  |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
2 | 1 | Basic Layout | Create navigation bar and initial layout of the app. |  |  |  | High | 21
2.1 |  | Create project | Create new vaadin project with all configurations | All | Tim | Raphael |  | 4 |  |  | waiting
2.2 |  | Database | Create database with all tables | Database | Rajilatha | Raphael |  | 4 |  |  | waiting
2.3 |  | View template | Create a view template, which can be used for all pages | UI | Tim | Nikola |  | 5 |  |  | waiting
2.4 |  | Navigation bar | Create the navigation bar | UI | Ueli | Nikola |  | 5 |  |  | waiting
2.5 |  | Main Controller | Create the controller for the home page and make the connection to the view | UI, Controller | Christoph | Rajilatha |  | 3 |  |  | waiting
4 | 1 | Patient Info Page | Display all the specified information about the patient |  |  |  | High | 16
4.1 |  | Create UI | Create the view to display all patient informations | UI | Nikola | Rajilatha |  | 5 |  |  | waiting
4.2 |  | Create controller | Create the controller for the Patient-view | Controller, UI | Raphael | Ueli |  | 4 |  |  | waiting
4.3 |  | Show patient informations | Properly read the data of the patient from the database and display them in the view | Database, Controller, UI | Rajilatha | Ueli |  | 5 |  |  | waiting
4.4 |  | Show task list | Properly read the tasklist of the patient from the database and display them in the view | Database, controller, UI | Ueli | Christoph |  | 2 |  |  | waiting
6 | 1 | Patient Report Page | Form to fill in after every visit |  |  |  | High | 17
6.1 |  | Create UI | Creating a new view with all UIcomponents, that the employee can write the report about the patients | UI | Raphael | Christoph |  | 5 |  |  | waiting
|  | Create controller | Create the controller for the Report-view |  | Nikola | Tim |  | 4 |  |  | waiting
6.2 |  | Response after saving | Poping up a message that the report is succesfuly saved. | UI,Controller | Ueli | Tim |  | 2 |  |  | waiting
6.3 |  | Saving the report | Properly saving the data from the report into the database | Database | Christoph | Tim |  | 3 |  |  | waiting
6.4 |  | Update the report | Posibility to edit and view the report | Database | Christoph | Raphael |  | 3 |  |  | waiting

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180