## ProjectTeam
Name | GitHub Alias
Bühler Ueli | smowdy
Jahn Tim Allan | ceoy
Kandiah Rajilatha | raji98
Klembowski Raphael | DerRaphe
Ristic Nikola | nristicBFH
Sutter Christoph | suttc1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
1 | User administration | The user has to login to use the app | low | 10 | 10 | 8 | done
2 | Landing Page | The day overview, the health visitor will see after a successful login | high | 38 | 38 | 34 | done
3 | Appointment Info Page | Display all the specified information about the patient | high | 16 | 16 | 16 | done
4 | Navigation | Handover of the necessary data to google maps for navigation | med | 8 | 8 | 4 | done
5 | Patient Report Page | Form to fill in after every visit | high | 17 | 19 | 16 | done
6 | Patient Report History | Display the history of all the reports of a specific patient | med | 20 | 15 | 12 | done
7 | Patient Evaluation | Form to fill in to create an evaluation | med | 20 | 20 | 16 | done
8 | Patient Evaluation History | Display the history of all evaluations of a specific patient | med | 15 | 20 | 20 | waiting
|  |  |  | 144 | 146 | 126

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Actual | Status
2 | 1 | Landing Page | The day overview, the health visitor will see after a successful login |  |  |  | High | 38 | 34 | done
2.1 | 1 | Create project | Create new vaadin project | All | Tim | Raphael |  | 4 | 3 | done
2.2 | 1 | Configurations | Set up the project configurations | All | Tim | Raphael |  | 4 | 3 | done
2.3 | 1 | Database | Create database with all tables | Database | Rajilatha | Nikola |  | 4 | 5 | done
2.4 | 1 | View template | Create a view template, which can be used for all pages (basic layout) | UI | Rajilatha | Nikola |  | 4 | 5 | done
2.5 | 1 | Navigation bar | Create the navigation bar (basic layout) | UI | Ueli | Christoph |  | 4 | 3 | done
2.6 | 1 | Main Controller | Create the controller for the home page and make the connection to the view (basic layout controller) | UI, Controller | Ueli | Christoph |  | 4 | 2 | done
2.7 | 1 | Create UI | Creating a new view with all UI components for the day overview | UI | Raphael | Rajilatha |  | 4 | 4 | done
2.8 | 1 | Day overview model | Create the data model for the day overview | Model | Raphael | Rajilatha |  | 1 | 2 | done
2.9 | 1 | Create controller | Create the controller for the Landing-page | Controller | Raphael | Tim |  | 4 | 3 | done
2.1 | 1 | Show appointments of the day | Properly read all appointments of the user of the day and show them in the view | UI,Controller | Nikola | Tim |  | 4 | 3 | done
2.11 | 1 | Mock data | Add some mock data to the database | Database | Tim | Ueli |  | 1 | 1 | done
3 | 1 | Appointment Info Page | Display all the specified information about the appointment |  |  |  | High | 16 | 16 | done
3.1 | 1 | Create UI | Create the view to display all informations to the appointment | UI | Nikola | Ueli |  | 4 | 5 | done
3.2 | 1 | Appointment model | Create the data model for the appointment | Model | Nikola | Raphael |  | 1 | 1 | done
3.3 | 1 | Create controller | Create the controller for the Appointment-view | Controller, UI | Christoph | Raphael |  | 4 | 4 | done
3.4 | 1 | Show appointment informations | Properly read the data of the appointment from the database and display them in the view | Database, Controller, UI | Christoph | Nikola |  | 4 | 3 | done
3.5 | 1 | Show task list | Properly read the tasklist of the appointment from the database and display them in the view | Database, controller, UI | Christoph | Nikola |  | 1 | 1 | done
3.6 | 1 | Link to patient page | Create a link from the landing page to the Appointment info page | UI | Ueli | Christoph |  | 1 | 1 | done
3.7 | 1 | Mock data | Add some mock data for the tasks and appointments to the database | Database | Rajilatha | Christoph |  | 1 | 1 | done
4 | 1 | Navigation | Handover of the necessary data to google maps for navigation |  |  |  | med | 8 | 4
4.1 | 1 | Prepare informations | Prepare the information for google maps | UI | Nikola | Ueli |  | 4 | 2 | done
4.2 | 1 | Handover data to google maps | Handover of the necessary data to google maps | Model | Nikola | Raphael |  | 4 | 2 | done
5 | 2 | Patient Report Page | Form to fill in after every visit |  |  |  | High | 19 | 16
5.1 | 2 | Create UI | Creating a new view with all UI components, that the employee can create a report for the patient | UI | Tim | Christoph |  | 4 | 4 | done
5.2 | 2 | Create controller | Create the controller for the Report-view | Controller | Tim | Christoph |  | 1 | 1 | done
5.3 | 2 | Response after saving | Poping up a message that the report is succesfuly saved. | UI,Controller | Tim | Christoph |  | 2 | 2 | done
5.4 | 2 | Saving the report | Properly saving the data from the report into the database | Database | Tim | Raphael |  | 2 | 3 | done
5.5 | 2 | Update the report | Posibility to edit and view the report | UI, Database | Ueli | Raphael |  | 2 | 1 | done
5.6 | 2 | Finishing the report | Change state of the report to "finished", that the fields are readonly | Controller, UI | Ueli | Raphael |  | 4 | 2 | done
5.7 | 2 | Mock data | Add some mock data to the database | Database | Rajilatha | Nikola |  | 4 | 3 | done
6 | 2 | Patient Report History | Display the history of all the reports of a specific patient |  |  |  | med | 15 | 12 | done
6.1 | 2 | Create UI for history | Creating a new view with all UI components, for showing all reports of the patient | UI | Raphael | Nikola |  | 4 | 1 | done
6.2 | 2 | Design UI | Make the UI user friendly | UI | Christoph | Nikola |  | 1 | 1 | done
6.3 | 2 | Button Icons | Binding Icons to the buttons | UI | Rajilatha | Tim |  | 1 | 1 | done
6.4 | 2 | Create UI for the reports view | Creating a new view with all UI components, for showing a report of the patient | UI | Raphael | Tim |  | 4 | 4 | done
6.5 | 2 | Update controller | update the controller for showing the Report history | Controller | Raphael | Tim |  | 1 | 3 | done
6.6 | 2 | Mock data | Add some mock data to the database | Database | Rajilatha | Ueli |  | 4 | 2 | done
7 |  | Patient Evaluation | Form to fill in to create an evaluation |  |  |  | med | 20 | 16 | done
7.1 | 2 | Create UI for evaluation landing page | Creating a new view with all UI components, for showing all open evaluations | UI | Nikola | Ueli |  | 4 | 2 | done
7.2 | 2 | Create UI for the evaluation Create-page | Creating a new view with all UI components, for creating a evaluation of a patient | UI | Nikola | Ueli |  | 4 | 4 | done
7.3 | 2 | Design evaluation landing page | Make the UI user friendly | UI | Ueli | Rajilatha |  | 2 | 2 | done
7.4 | 2 | Design evaluation creation page | Make the UI user friendly | UI | Christoph | Rajilatha |  | 4 | 2 | done
7.5 | 2 | Button Icons | Binding Icons to the buttons | UI | Ueli | Rajilatha |  | 1 | 1 | done
7.6 | 2 | Create methods | Update the controller for showing the Report history | Controller | Nikola | Christoph |  | 1 | 2 | done
7.7 | 2 | Mock data | Add some mock data to the database | Database | Christoph | Raphael |  | 4 | 3 | done
1 |  | User administration | The user has to login to use the app |  |  |  | med | 10 | 10 | done
1.1 | 2 | Create UI for a login page | Creating a new view with all UI components, for showing all open evaluations | UI | Nikola | Raphael |  | 2 | 1 | done
1.2 | 2 | Add users to database | Add some users to database | Databse | Christoph | Raphael |  | 2 | 2 | done
1.3 | 2 | Implement authentication | Implement the autentication | Controller | Ueli | Tim |  | 4 | 4 | done
1.4 | 2 | Make admin view | Creating a view only for Admin-Users | UI, Controller | Rajilatha | Tim |  | 2 | 3 | done
8 |  | Patient Evaluation History | Display the history of all evaluations of a specific patient |  |  |  | med | 20 |  | waiting
8.1 | 3 | Create UI for history | Creating a new view with all UI components, for showing all evaluations of the patient | UI |  | Tim |  | 4 |  | waiting
8.2 | 3 | Design UI | Make the UI user friendly | UI |  | Ueli |  | 4 |  | waiting
8.3 | 3 | Button Icons | Binding Icons to the buttons | UI |  | Christoph |  | 2 |  | waiting
8.4 | 3 | Create UI for the reports view | Creating a new view with all UI components, for showing a evaluation of the patient | UI |  | Nikola |  | 4 |  | waiting
8.5 | 3 | Update controller | Update the controller for showing the evaluation history | Controller |  | Raphael |  | 4 |  | waiting
|  | Mock data | Add some mock data to the database | Database |  | Rajilatha |  | 2 |  | waiting

## BurndownChart
Sprint | Sprint ID | Time of Record | Remaining Effort | Remaining Ressources | Working Time
1 | 1 | 2019-05-08 | 36 | 32 | 4
1 | 1 | 2019-05-10 | 32 | 24 | 8
1 | 1 | 2019-05-12 | 24 | 5 | 19
1 | 1 | 2019-05-13 | 5 | 0 | 5
1 | 2 | 2019-05-13 | 16 | 12 | 4
1 | 2 | 2019-05-15 | 12 | 5 | 7
1 | 2 | 2019-05-16 | 7 | 0 | 7
2 | 2 | 2019-05-20 | 54 | 42 | 12
2 | 2 | 2019-05-22 | 42 | 38 | 4
2 | 2 | 2019-05-23 | 38 | 34 | 4
2 | 2 | 2019-05-24 | 34 | 22 | 12
2 | 2 | 2019-05-26 | 22 | 14 | 8
2 | 2 | 2019-05-27 | 14 | 10 | 4
2 | 2 | 2019-05-28 | 10 | 3 | 7
2 | 2 | 2019-05-31 | 3 | 0 | 3