## ProjectTeam
Name | GitHub Alias
Bühler Ueli | smowdy
Jahn Tim Allan | ceoy
Kandiah Rajilatha | raji98
Klembowski Raphael | DerRaphe
Ristic Nikola | nristicBFH
Sutter Christoph | suttc1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | User administration | The user has to login to use the app | low | 10 | 10h | 0h | waiting
2 | Landing Page | The day overview, the health visitor will see after a successful login | high | 38 |  |  | waiting
3 | Appointment Info Page | Display all the specified information about the patient | high | 16 |  |  | waiting
4 | Navigation | Handover of the necessary data to google maps for navigation | med | 8 |  |  | waiting
5 | Patient Report Page | Form to fill in after every visit | high | 17 |  |  | waiting
6 | Patient Report History | Display the history of all the reports of a specific patient | med | 20 |  |  | waiting
7 | Patient Evaluation | Form to fill in to create an evaluation | med | 20 |  |  | waiting
8 | Patient Evaluation History | Display the history of all evaluations of a specific patient | med | 15 |  |  | waiting
144

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
2 | 1 | Landing Page | The day overview, the health visitor will see after a successful login |  |  |  | High | 38
2.1 | 1 | Create project | Create new vaadin project | All | Tim | Raphael |  | 4 |  |  | waiting
2.2 | 1 | Configurations | Set up the project configurations | All | Tim | Raphael |  | 4 |  |  | waiting
2.3 | 1 | Database | Create database with all tables | Database | Rajilatha | Nikola |  | 4 |  |  | waiting
2.4 | 1 | View template | Create a view template, which can be used for all pages (basic layout) | UI | Rajilatha | Nikola |  | 4 |  |  | waiting
2.5 | 1 | Navigation bar | Create the navigation bar (basic layout) | UI | Ueli | Christoph |  | 4 |  |  | waiting
2.6 | 1 | Main Controller | Create the controller for the home page and make the connection to the view (basic layout controller) | UI, Controller | Ueli | Christoph |  | 4 |  |  | waiting
2.7 | 1 | Create UI | Creating a new view with all UI components for the day overview | UI | Raphael | Rajilatha |  | 4 |  |  | waiting
2.8 | 1 | Day overview model | Create the data model for the day overview | Model | Raphael | Rajilatha |  | 1 |  |  | waiting
2.9 | 1 | Create controller | Create the controller for the Landing-page | Controller | Raphael | Tim |  | 4 |  |  | waiting
2.1 | 1 | Show appointments of the day | Properly read all appointments of the user of the day and show them in the view | UI,Controller | Nikola | Tim |  | 4 |  |  | waiting
2.11 | 1 | Mock data | Add some mock data to the database | Database | Tim | Ueli |  | 1 |  |  | waiting
3 | 1 | Appointment Info Page | Display all the specified information about the appointment |  |  |  | High | 16
3.1 | 1 | Create UI | Create the view to display all informations to the appointment | UI | Nikola | Ueli |  | 4 |  |  | waiting
3.2 | 1 | Appointment model | Create the data model for the appointment | Model | Nikola | Raphael |  | 1 |  |  | waiting
3.3 | 1 | Create controller | Create the controller for the Appointment-view | Controller, UI | Christoph | Raphael |  | 4 |  |  | waiting
3.4 | 1 | Show appointment informations | Properly read the data of the appointment from the database and display them in the view | Database, Controller, UI | Christoph | Nikola |  | 4 |  |  | waiting
3.5 | 1 | Show task list | Properly read the tasklist of the appointment from the database and display them in the view | Database, controller, UI | Christoph | Nikola |  | 1 |  |  | waiting
3.6 | 1 | Link to patient page | Create a link from the landing page to the Appointment info page | UI | Ueli | Christoph |  | 1 |  |  | waiting
3.7 | 1 | Mock data | Add some mock data for the tasks and appointments to the database | Database | Rajilatha | Christoph |  | 1 |  |  | waiting
7 | 2 | Patient Report Page | Form to fill in after every visit |  |  |  | High | 17
7.1 | 2 | Create UI | Creating a new view with all UIcomponents, that the employee can write the report about the patients | UI |  |  |  | 4 |  |  | waiting
7.2 | 2 | Create controller | Create the controller for the Report-view |  |  |  |  | 4 |  |  | waiting
7.3 | 2 | Response after saving | Poping up a message that the report is succesfuly saved. | UI,Controller |  |  |  | 2 |  |  | waiting
7.4 | 2 | Saving the report | Properly saving the data from the report into the database | Database |  |  |  | 3 |  |  | waiting
7.5 | 2 | Update the report | Posibility to edit and view the report | Database |  |  |  | 3 |  |  | waiting
7.6 | 2 | Mock data | Add some mock data to the database | Database |  |  |  | 1 |  |  | waiting

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180